## TimeLine
|  | 2025-01-01 | 2025-01-02 | 2025-02-01 | 2025-02-02 | 2025-03-01 | 2025-03-02 | 2025-04-01 | 2025-04-02 | 2025-05-01 | 2025-05-02 | 2025-06-01 | 2025-06-02 | 2025-07-01 | 2025-07-02 | 2025-08-01 | 2025-08-02 | 2025-09-01 | 2025-09-02 | 2025-10-01 | 2025-10-02 | 2025-11-01 | 2025-11-02 | 2025-12-01 | 2025-12-02
Key: | Planning | bar: 2025-01-01 to 2025-02-01
Significant Events = | Building My Website | bar: 2025-02-01 to 2025-03-01
Personal Milestones = | Working on my 3000 project | bar: 2025-02-01 to 2025-03-02
Submission = | Connecting and using linkden
Working on = | Working on online certificats | bar: 2025-03-02; 2025-04-02
Yet to start = | Write on my blog | bar: 2025-01-01 to 2025-03-02; 2025-04-02 to 2025-05-01
Time off = | Read up on useful resources
Completed = | Attend events
Poster for 3000 | bar: 2025-03-01 to 2025-03-02
Showcase event for 3000 | bar: 2025-05-01
Sweat code wars | bar: 2025-02-01 to 2025-03-02; 2025-04-02 to 2025-12-02

## RoadMap
Key = | Red = Milestone | Orange = Urgant
Black = Not finished
Epic | User Story | Tasks (all of these on trello) | 2025-03-02 | 2025-10-02 | 17/2/2025 | 24/2/2025 | 2025-03-03 | 2025-10-03 | 17/3/2025 | 24/3/2025
Setup and Planning
SWOT
MindMap
User Story Map
Submission ready
Creating Portfolio Website
Research into what makes a good portfolio website
Find online resources (Youtube, blogs,etc)
Create the website
Find a way to make the website go live
Add to the webstie when final year project is complete
3000 Game
Complete Game
Carry out User Testing
Create Poster
Showcase
Strengthen Coding Skills
Code Wars
Online Courses
Linkden

## RoadMap2
[5 empty] | Feb |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August | September
Key | Colour | Epic | User Story | Tasks | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2002-06-01 | 2009-06-01 | 2016-06-01 | 2023-06-01 | 1930-06-01 | 2007-07-01 | 2014-07-01
Research Tasks |  | Plan the year ahead
Design Tasks |  |  | SWOT / Mind Map
Dev Tasks |  |  | User Story Map
Deployment tasks |  |  | RoadMap
Completed Tasks |  |  | TimeLine
InProgres: |  |  | Trello
Plan Doc
Portfolio Website
Research/Planning
Youtube Videos/Tutorial
Find examples
Create Website
Design site
Fill it with content
Make the website go live
Figure out how to host the website
Host and pay for the site to be live (12 months?)
Timeline Takedown (3000)
Project Poster
Plan out the design and content that will be on the poster
Gather all the needed content for the poster (Screenshots, art work)
Create the poster and get feedback
Print Poster and Submit
Complete the Game
Sprint 4
Sprint 5
Sprint 6
Sprint 7
Sprint 8
Sprint 9
Turn into a game
Showcase
Gather all materials needed for showcase
Create Script/practice what I will say/talk about
Business Cards
Create Content For Website
Utilise Code ninja
Do code ninja most days, earn levels and certificates to display on website and to strengthen coding skills
Earn online certificates to display on website and linkden
..
..